Quantum-Resistant Cryptography

Migration Plan — Q3 2026

Internal Engineering — Confidential

Prepared by: Dr. Priya Subramanian, Principal Cryptographer

Approved: May 28, 2026

# 1. Executive Summary

This document describes the plan to migrate our internal and customer-facing systems from RSA-2048 and ECDSA-P256 to post-quantum cryptographic (PQC) algorithms standardized by NIST in 2024. Migration begins July 15, 2026 and is scheduled to complete by Q2 2027.

The total approved budget is $4,200,000 USD, allocated across four phases. The migration affects 47 internal services and 12 customer-facing APIs. The primary lead is Dr. Priya Subramanian; technical execution is shared across the Platform Security team (12 engineers) and the Cloud Infrastructure team (9 engineers).

## 1.1 Rationale

Recent improvements in error-corrected quantum computing — particularly the demonstration of a 1,121 logical qubit system in late 2025 — have shortened the public estimates of when a cryptographically-relevant quantum computer might exist. NIST and CISA recommend completion of PQC migration for high-value systems by 2030. Our internal threat model (which assumes harvest-now-decrypt-later attacks on PII) targets completion by mid-2027.

# 2. Threat Model

We assume a well-funded adversary with the capabilities outlined below.

| Capability | Available (today) | Assumed by 2030 |
| --- | --- | --- |
| Harvest-now-decrypt-later (HNDL) | Yes | Yes |
| Side-channel analysis on edge devices | Yes | Yes |
| Shor's algorithm at 4,000 logical qubits | No (~1,100 today) | Plausible |
| Grover's algorithm on 128-bit ciphers | No | Not material (PQC sym keys widened to 256-bit) |
| Quantum random number prediction | No | No |

Our migration must therefore protect data with confidentiality requirements extending past 2030. This includes anything in our customer database covered by GDPR, HIPAA, or our 7-year contractual retention obligations.

# 3. Algorithm Selection

We are adopting the NIST-standardized PQC algorithms finalized in August 2024:

| Purpose | Selected Algorithm | Public Key | Ciphertext / Signature |
| --- | --- | --- | --- |
| Key encapsulation | ML-KEM-768 (formerly CRYSTALS-Kyber) | 1,184 bytes | 1,088 bytes |
| Digital signature | ML-DSA-65 (formerly CRYSTALS-Dilithium) | 1,952 bytes | 3,309 bytes |
| Hash-based signature (long-term roots) | SLH-DSA-SHA2-128s (formerly SPHINCS+) | 32 bytes | 7,856 bytes |

Note: The selected key encapsulation algorithm is ML-KEM-768, formerly known as CRYSTALS-Kyber. This is the algorithm referenced throughout this document as our "primary KEM."

## 3.1 Hybrid Period

During the migration window we operate in hybrid mode: a TLS handshake establishes session keys using BOTH classical (X25519) and PQC (ML-KEM-768) key exchanges, with the final session key derived by HKDF over both shared secrets. This guarantees backwards compatibility with non-PQC clients and zero downgrade attack surface.

# 4. Migration Phases

| Phase | Name | Start Date | End Date | Budget |
| --- | --- | --- | --- | --- |
| 1 | Internal Inventory + Discovery | July 15, 2026 | August 31, 2026 | $320,000 |
| 2 | Internal Services Migration | September 1, 2026 | December 19, 2026 | $1,450,000 |
| 3 | Customer-facing API Migration | January 5, 2027 | April 17, 2027 | $1,830,000 |
| 4 | Decommission Classical Algorithms | April 20, 2027 | June 30, 2027 | $600,000 |

Phase 1 begins on July 15, 2026 — this is the migration kickoff date for the entire program. All scheduling references in this document anchor to that date.

## 4.1 Phase 1 Detail

Phase 1 performs a complete cryptographic inventory: every TLS certificate, every signing key, every encrypted-at-rest blob. We tag each artifact with one of three migration paths — hybrid, in-place replacement, or deprecation.

## 4.2 Phase 2 Detail

Phase 2 covers the 47 internal services. Each service team receives a dedicated PQC liaison from the Platform Security team. Services migrate in order of criticality: tier-1 (auth, billing) first; tier-3 (internal dashboards) last.

## 4.3 Phase 3 Detail

Phase 3 covers the 12 customer-facing APIs. We will offer customers a 90-day overlap during which both the classical and PQC endpoints accept requests, with a deprecation notice emitted on every classical request.

## 4.4 Phase 4 Detail

Phase 4 removes the classical key exchange and signing paths. Production cipher suites are restricted to PQC-only or hybrid (no classical-only). All RSA-2048 and ECDSA-P256 keys are rotated to ML-KEM-768 / ML-DSA-65 equivalents.

# 5. Risk Assessment

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Customer client libraries don't support PQC | High | Medium | Hybrid mode; vendor outreach starting July 2026 |
| R2 | ML-KEM-768 ciphertext size breaks legacy MTU assumptions | Medium | Medium | Path MTU testing during Phase 2 |
| R3 | Performance regression on edge devices (ARM Cortex-M) | Medium | High | Hardware acceleration shim; benchmark gating |
| R4 | NIST standard amendments between 2026 and migration completion | Low | High | Algorithm-agility framework abstracting algorithm choice |
| R5 | Side-channel leakage in our reference implementation | Medium | High | External audit by Trail of Bits; constant-time implementation |
| R6 | Key escrow / regulatory pushback in EU markets | Low | Medium | Legal review in Q4 2026 |

# 6. Team and Responsibilities

| Role | Owner | Headcount |
| --- | --- | --- |
| Principal Cryptographer | Dr. Priya Subramanian | 1 |
| Platform Security Team | Marcus Chen (Director) | 12 |
| Cloud Infrastructure Team | Sara Lindqvist (Director) | 9 |
| Security Operations Liaison | Tomás Reyes | 2 |
| External Auditor | Trail of Bits | Contract — 3 reviewers |
| Customer Success Coordinator | Olivia Kapoor | 1 |
| Executive Sponsor | CTO (Janice Akabu) | 1 |

Total internal headcount allocated to the migration: 26 engineers and managers, plus 1 contracted audit team.

# 7. Budget Detail

| Category | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total |
| --- | --- | --- | --- | --- | --- |
| Engineering labor | $200,000 | $950,000 | $1,200,000 | $400,000 | $2,750,000 |
| External audit | $80,000 | $200,000 | $170,000 | $50,000 | $500,000 |
| Tooling and licenses | $25,000 | $150,000 | $250,000 | $50,000 | $475,000 |
| Customer outreach | $5,000 | $30,000 | $120,000 | $30,000 | $185,000 |
| Reserve / contingency | $10,000 | $120,000 | $90,000 | $70,000 | $290,000 |
| Total | $320,000 | $1,450,000 | $1,830,000 | $600,000 | $4,200,000 |

Total program budget: $4,200,000 USD, fully approved by the Board on May 14, 2026, with quarterly reviews and a hard cap of 8% overrun before re-approval is required.

# 8. Timeline Milestones

| Milestone | Target Date | Owner |
| --- | --- | --- |
| Phase 1 kickoff | July 15, 2026 | Dr. Subramanian |
| Cryptographic inventory complete | August 31, 2026 | Platform Security |
| First internal service on hybrid | September 21, 2026 | Cloud Infra |
| 50% of internal services migrated | November 7, 2026 | Platform Security |
| All internal services migrated | December 19, 2026 | Platform Security |
| Customer beta program opens | January 12, 2027 | Customer Success |
| 50% of customer APIs on PQC | February 28, 2027 | Cloud Infra |
| All customer APIs on PQC | April 17, 2027 | Cloud Infra |
| Classical algorithms decommissioned | June 30, 2027 | Platform Security |
| Final external audit report | August 15, 2027 | Trail of Bits |

# 9. Affected Systems Summary

This migration touches a total of 59 systems. They break down as:

- 47 internal services (authentication, billing, messaging, observability, dashboards, etc.)

- 12 customer-facing APIs (REST APIs at api.example.com, GraphQL at graph.example.com)

## 9.1 Internal Service Categories

| Tier | Description | Count |
| --- | --- | --- |
| Tier 1 | Authentication, identity, billing | 8 |
| Tier 2 | Order management, customer messaging, audit | 17 |
| Tier 3 | Internal dashboards, reporting, analytics | 14 |
| Tier 4 | Development and test environments | 8 |

# 10. Plan Acceptance

This plan, dated May 28, 2026, supersedes the discussion draft circulated in February 2026. Material changes from the draft include: budget increased from $3.8M to $4.2M, primary lead changed from CTO to Dr. Priya Subramanian, and the customer-facing migration window extended by 30 days.

Approvals:

Principal Cryptographer: Dr. Priya Subramanian  •  Approved 2026-05-28

CTO: Janice Akabu  •  Approved 2026-05-28

CISO: Robert Tatum  •  Approved 2026-05-28

Board of Directors  •  Approved 2026-05-14 (budget); ratification 2026-06-04 (full plan)